## Project plan
Project plan template · projektiassistent.ee — Rather not fill in a blank template? Describe your project in a few sentences and AI drafts the plan, schedule, budget and risks (14 days free) →
Guide and filled-in example: projektiassistent.ee/en/project-plan/
Plan section | What to write | Your project
1. Title and summary | One paragraph: what is being done, for whom, by when and at what cost. The only part everyone definitely reads.
2. Background and problem | What the situation is now and why it does not work. Use a number, not an adjective: \"processing takes 21 days\", not \"processing is slow\".
3. Objectives and success criteria | A measurable target: what changes, by how much and by when. Each objective has to say how it will be measured afterwards.
4. Scope and boundaries | What is inside the project and — just as important — what is out. The out-of-scope list is what stops scope creep later.
5. Deliverables | The concrete things that exist when the project ends: a system, equipment, trained people, a document, a permit.
6. Activity plan and phases | The project split into phases and activities. Every activity ties to an objective; an activity that does not is probably surplus.
7. Schedule and milestones | Start, end, phase deadlines and dependencies. A milestone is a point where something is checked, not just a date.
8. Team and responsibility | Who leads, who does the work, who approves and who needs to know. One owner per activity, not three.
9. Budget | Cost lines per activity, net amounts with VAT separated, co-financing and funding sources.
10. Resources | People and their workload, equipment, premises, licences, bought-in work.
11. Risks and mitigation | For each risk: impact, probability, mitigation and owner. Five thought-through rows beat twenty generic ones.
12. Stakeholders and communication | Who the project affects, what they need to know and who talks to them.
13. Metrics and reporting | What is tracked during the project, how often and who it is reported to.

## Action plan
Project plan template · projektiassistent.ee — Rather not fill in a blank template? Describe your project in a few sentences and AI drafts the plan, schedule, budget and risks (14 days free) →
Guide and filled-in example: projektiassistent.ee/en/project-plan/
No. | Activity | Owner | Start | End | Duration (d) | Depends on (no.) | Deliverable | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Budget
Project plan template · projektiassistent.ee — Rather not fill in a blank template? Describe your project in a few sentences and AI drafts the plan, schedule, budget and risks (14 days free) →
Guide and filled-in example: projektiassistent.ee/en/project-plan/
VAT rate | 24%
Cost line | Activity (no.) | Quantity | Unit price (net) | Net | VAT | Gross | Funding source
Total

## Risks
Project plan template · projektiassistent.ee — Rather not fill in a blank template? Describe your project in a few sentences and AI drafts the plan, schedule, budget and risks (14 days free) →
Guide and filled-in example: projektiassistent.ee/en/project-plan/
Score = likelihood × impact. 15+ is red: that risk needs a mitigation and an owner.
Risk | Likelihood (1–5) | Impact (1–5) | Score | Mitigation | Owner | Status